## Calendar
Board Meeting Schedule
Year/Frequency | Details | Method
WORKING BOARD (Jun 2017 - Aug 2018 / Incubation year)
Every Tuesday | 20:00 | Phone
Every Saturday | 7:30 | In person / Phone
GOVERNING BOARD (Aug 2018 - Jun 2019)
Bi-weekly |  | In person / Phone
Monthly | Official | In person (required)
Monthly (prior to BOD) | Committees | In person
GOVERNING BOARD (Jun 2019 - Ongoing)
Monthly | Official | In person
Monthly (prior to BOD) | Committees | In person
In addition to above, meetings can be called outside of these and as needed
Meeting Agenda Schedule
Delegated to | Tab
Working Board | "Start-up plan"
Governing Board | "Tasks 2018 - 2019"

## Start-up Plan (2017-2018)
Task | Start date | Deadline | Owners | Notes
Finance & Budget
Finalize YR0 budget and 4-year plan | 2017-02-17 | 2017-09-17 | DT
Finalize YR1 budget | 2017-11-17 | 2017-12-17 | BM
Revisit assumptions and ensure they are still valid | 2017-05-18 | 2017-06-18 | BM/P
Develop 5-yr contingency budgets | 2017-01-18 | 2017-03-18 | BM | Include moderate and conservative enrollment, fundraising scenarios; include HS extension
Establish line of credit | 2017-12-18 |  | BM | Upon approval
Open bank accounts and order checks | 2017-01-18 |  | BM | Upon approval
Identify check writers and signatories | 2017-01-18 |  | BM | Upon approval
Purchase and implement accounting software | 2017-12-18 | 2017-01-18 | BM
Select & hire accounting firm | 2017-11-17 | 2017-01-18 | DT/BM | Final decision with BM
Develop standard forms (POs, contracts) | 2017-12-18 | 2017-01-18 | BM
Develop formats for monthly financial reports for the board | 2017-12-18 | 2017-01-18 | BM/DT
Build detailed procurement list by item | 2017-12-18 | 2017-03-18 | BM/DT
Build list of vendors and obtain quotes | 2017-12-18 | 2017-03-18 | BM/DT
Obtain insurance policy | 2017-12-18 |  | BM/DT | Upon approval – advised by Drew Sandler (CAMM)
Confirm auditing process | 2017-09-17 | 2017-01-18 | DT | Engage upon approval, begin discussion in the fall of 2017
Define process for student billing | 2017-03-18 | 2017-04-18 | BM
Set up credit cards for school leadership | 2017-02-18 | 2017-03-18 | DT
Arrange payroll system | 2017-12-17 | 2017-01-18 | DT | Paylocity is the recommended provider by OneDigital (insurance broker)
Finalize process for financial controls: reimbursements, approvals, accounting, monitoring, expenditures, reporting | 2017-12-17 | 2017-01-18 | BM/DT
Finalize all fiscal policies | 2017-01-18 | 2017-04-18 | BM/DT
Task | Start date | Deadline | Owners | Notes
Facilities
Facility feasibility analysis | 2017-12-16 | 2017-02-17 | IFF | Report in Appendix 4.3
Identify potential school sites | 2017-02-16 | 2017-09-17 | DT | Contracted Marc Realty and will continue to engage IFF for site assessment
Identify renovations most conducive of learning with an approved architect | 2017-09-17 | 2017-12-17 | DT | Including space usage plan
Draft lease and MOU | 2017-09-17 | 2017-12-17 | DT
Identify project manager for facility | 2017-09-17 | 2017-12-17 | DT
Create a timeline for improvements/code compliance | 2017-12-17 | 2017-01-18 | DT
Necessary facility inspections initiated including ADA review | 2017-06-18 | 2017-07-18 | DT
Complete ADA accountability report | 2017-06-18 | 2017-07-18 | DT
Solicit bids for renovations and improvements | 2017-11-17 | 2017-01-18 | DT
Begin zoning process |  |  |  | Focusing on facilities that are already zoned appropriately, but will move quickly to get a zoning permit if needed
Obtain zoning approval
File construction permit | 2017-12-17 | 2017-01-17 | DT | We have been advised to allow 8 weeks for permit approval
Conduct renovations | 2017-02-18 | 2017-06-18 | DT | DT would oversee contractors
Schedule building permit & certificate of occupancy inspections | 2017-06-18 | 2017-07-18 | DT
Ensure facility plans comply with City of Chicago building code for schools | 2017-12-17 | 2017-01-18 | DT
Establish property insurance | 2017-02-17 | 2017-01-18 | DT | Working with Drew Sandler/KAMM Insurance group for projected needs and expenses
Address building security issues | 2017-05-18 | 2017-06-18 | BM/OM
Secure and install utility services | 2017-05-18 | 2017-06-18 | OM
Secure cleaning & maintenance services | 2017-05-18 | 2017-06-18 | FM
Order and set up furniture and equipment | 2017-05-18 | 2017-07-18 | BM/OM
Order & post school signage | 2017-06-18 | 2017-07-18 | OM
Liaise with local police for crosswalk | 2017-06-18 | 2017-06-18 | FM
Outline student/visitor traffic flows | 2017-06-18 | 2017-07-18 | P/FM
Develop comprehensive emergency response plan | 2017-06-18 | 2017-07-18 | P/OM
Establish evacuation plan for all rooms | 2017-06-18 | 2017-07-18 | P/OM
Train personnel in emergency preparedness | 2017-06-18 | 2017-07-18 | P/OM
Schedule and test fire drills | 2017-06-18 | 2017-07-18 | P/OM
Update school contact information into Facility and Information Mgmt System | 2017-06-18 | 2017-07-18 | OM
Update stakeholders on facility status and timeline | 2017-09-17 | 2017-06-18 | DT | Continuous feedback loop
Seek and find space co-share community partner | 2017-09-17 | 2017-03-18 | DT | For YR1-3
Task | Start date | Deadline | Owners | Notes
Student recruitment & enrollment (post approval; please see Community Outreach plan for pre-approval)
Finalize recruitment plan/campaign | 2017-11-17 | 2017-12-17 | DT | Recruitment plan builds on community engagement plan (04/17-12/17), which is available upon request
Develop advertising | 2017-09-17 | 2017-01-18 | DT | Launch advertising upon approval
Finalize/update student recruitment materials | 2017-11-17 | 2017-12-17 | DT | For post-approval recruitment
Develop mass mailing | 2017-09-17 | 2017-11-17 | DT | Mail upon approval
Develop plan and/or maps for door-to-door canvassing | 2017-09-17 | 2017-11-17 | DT | Launch upon approval
Launch and monitor student recruitment plan/campaign (advertise, distribute materials, send mailings, canvass, specialized students) | 2017-11-12 | 2017-04-18 | DT/P | Launch upon approval
Finalize application process | 2017-09-17 | 2017-11-17 | DT
Create student enrollment kit (info on school, family handbook, calendars, dress code, etc.) | 2017-04-18 | 2017-06-18 | DT/P | Material available online and in-print (in English and Spanish); will provide copies during family orientation
Finalize plan to ensure adequate recruitment of specialized students | 2017-09-17 | 2017-11-17 | DT | including those with special needs and/or are STLS/homeless
Prepare and hold lottery | 2017-03-18 | 2017-04-18 | DT/P
Notify families of lottery results | 2017-04-18 | 2017-04-18 | P | Lottery results will be mailed week
Schedule & hold information sessions for parents | 2017-04-18 | 2017-07-18 | P/DT | and incorporate into marketing materials
Obtain release of student records for transfer students | 2017-04-18 | 2017-08-18 | P/SC | Upon enrollment
Plan family and student orientation | 2017-06-18 | 2017-08-18 | P/A
Register all accepted students and enroll in CPS system (determine enrollment cut-off date) | 2017-04-18 | 2017-08-18 | P/SC
Align data in IMPACT and SIS | 2017-06-18 | 2017-08-18 | P/SC
Notify students on waitlist, register as appropriate | 2017-04-18 | 2017-08-18
Review IEP transportation needs | 2017-06-18 | 2017-08-18 | STT
Procure public transportation cards | 2017-06-18 | 2017-07-18 | OM
Develop car pool network & address transportation needs and questions | 2017-06-18 | 2017-07-18 | OM/SC
Hold family and student orientation | 2017-08-18 | 2017-08-18 | P/A | First Friday of school
Task | Start date | Deadline | Owners | Notes
Academics & curriculum development
Complete full alignment with ILSSS | 2017-11-17 | 2017-05-18 | P/DT | Full alignment will be completed prior to hiring teaching staff
Finalize alignment with ILS-Science | 2017-02-18 | 2017-06-18 | P/DT/CT | Principal in conjunction with the Design Team and select advisors will complete the alignment internally if the Core Knowledge Foundation is unable to complete by 09/18
Finalize Spanish curriculum | 2017-01-18 | 2017-07-18 | DT/ST | Board will provide Spanish teacher with its recommendation; final decision will remain with the teacher
Develop PE curriculum | 2017-04-18 | 2017-06-18 | DT/P/ST | PE curriculum will be based on the core philosophy of classical liberal-arts education; finalize with Physical Education teacher
Create and establish Child Find system in compliance with IDEA | 2017-06-18 | 2017-12-18 | P/STT | Coordinating with the District’s Child Find responsibilities
Task | Start date | Deadline | Owners | Notes
Governance
Grow Board membership | 2017-04-17 | 2017-12-17 | DT | Specifically: Academics, Development & Community Liaison
Form Family Advisory Board | 2017-12-17 | 2017-03-18 | DT | Will begin building possible membership 04/17; will start forming board upon approval; note: this board carries no governing authority
Finalize Board calendar for YR0 | 2017-04-17 | 2017-12-17 | DT
Finalize Board calendar for YR1 | 2017-04-18 | 2017-06-18 | DT
Finalize Board forms and procedures | 2017-04-18 | 2017-06-18 | DT
Plan and execute Board training | 2017-03-18 | 2017-06-18 | DT
Task | Start date | Deadline | Owners | Notes
Staff recruitment & selection
Finalize duties for YR0 | 2017-09-17 | 2017-12-17 | DT
Develop recruitment plan/hiring calendar | 2017-11-17 | 2017-01-18 | P/DT
Create staff recruitment marketing materials | 2017-11-17 | 2017-01-18 | DT
Hire Principal | 2017-09-17 | 2017-01-18 | DT
Train Principal & assign duties for Year 0 | 2017-01-18 | 2017-02-18 | DT | Including BCSI Principal training
Draft employee contracts with counsel | 2017-01-18 | 2017-02-18 | DT /P
Post job descriptions, advertise and recruit teachers and staff | 2017-01-18 | 2017-04-18 | P
Teacher interviews and site visits/referrals | 2017-04-18 | 2017-05-18 | P
Conduct background checks | 2017-04-18 | 2017-05-18 | P
Hire teachers & staff | 2017-04-18 | 2017-05-18 | P | See staffing model
Hire related service providers | 2017-06-18 | 2017-08-18 | P/BM | OM/FM will act in supporting role
Ensure all staff meet certification requirements | 2017-04-18 | 2017-05-18 | P
Train all teachers & staff | 2017-07-18 | 2017-08-18 | P/BCSI | See professional development calendar
Create & execute onboarding procedures for all staff | 2017-04-18 | 2017-07-18 | P/DT
Finalize professional development plan & curriculum | 2017-04-18 | 2017-06-18 | P/DT
Finalize office staff roles and responsibilities | 2017-06-18 | 2017-07-18 | P/DT
Hire insurance broker | 2017-01-18 | 2017-01-18 | DT | Being advised by Craig Stubler/OneDigital
Finalize benefits package design | 2017-01-18 | 2017-01-18 | DT
Obtain quotes for health benefits | 2017-01-18 | 2017-01-18 | DT
Secure health benefits package | 2017-01-18 | 2017-02-18 | DT
Prepare welcome materials to send upon hire | 2017-04-18 | 2017-05-18 | P/DT
Finalize school counselor roles and responsibilities | 2017-04-18 | 2017-06-18 | P
Post Business Manager job description and seek referrals | 2017-08-17 | 2017-12-17 | DT
Hire Business Manager | 2017-09-17 | 2017-01-18 | DT/P | Principal and Business Manager will be the first two hires
Post Special Education teacher job description and seek referrals | 2017-12-17 | 2017-05-18 | DT
Hire Special Education teacher | 2017-01-18 | 2017-06-18
Task | Start date | Deadline | Owners | Notes
School policies & procedures
Develop office operating procedures | 2017-04-18 | 2017-07-18 | P/BM/OM
Define visitor policy | 2017-06-18 | 2017-07-18 | OM
Phone answering | 2017-06-18 | 2017-07-18 | OM | Who is responsible and when
Define medical procedures/system | 2017-06-18 | 2017-07-18 | P/OM
Implement SIS and populate with data | 2017-03-18 | 2017-07-18 | P/OM
Finalize school calendar | 2017-01-18 | 2017-05-18 | P
Finalize master and bell schedule | 2017-04-18 | 2017-07-18 | P/SC | Begin finalizing after lottery
Adapt existing student & family handbook | 2017-03-18 | 2017-07-18 | P/OM
Finalize school manual for policies and procedures | 2017-03-18 | 2017-07-18 | P/OM
Design volunteer program | 2017-03-18 | 2017-06-18 | DT/P
Finalize Operational Plan | 2017-03-18 | 2017-07-18 | DT/P/BM
Finalize Safety Plan | 2017-06-18 | 2017-07-18 | DT/P/FM | Advised by Sgt. Dombrowski
Finalize Emergency Plan | 2017-06-18 | 2017-07-18 | DT/P/FM | Advised by Sgt. Dombrowski
Solicit vendor and negotiate contract (supplies, furniture, curriculum, playground, equipment, uniforms) | 2017-03-18 | 2017-06-18 | BM/DT
Coordinate with local law enforcement for fire drills and evacuation procedures | 2017-05-18 | 2017-06-18 | BM/DT
Coordinate/ensure pick up and drop off safety | 2017-06-18 | 2017-07-18 | FM
First aid training for relevant staff | 2017-08-18 | 2017-08-18 | OM
Revisit and ensure process to meet CPS requirements | 2017-04-18 | 2017-08-18 | P/DT | Continuing process as material/procedures are finalized and students are enrolled
Determine transportation needs based on enrollment | 2017-04-18 | 2017-08-18 | P/STT | Continue evaluation throughout the enrollment process to ensure all needs are addressed (including any IEP requirements)
Task | Start date | Deadline | Owners | Notes
Fundraising & grant writing
Apply for electronic Charter Schools Program - QSO Program Design and Initial Implementation | 2017-03-17 | 2017-07-17 | DT
Design and launch fundraising plan for start-up | 2017-03-17 | 2017-10-17 | DT
Research available grants and apply | 2017-01-17 | Ongoing | DT | Deadlines based on grant specific deadlines
Confirm donor commitments | 2017-10-17 | 2017-11-17 | DT
Develop Associate Board | 2017-05-17 | 2017-09-17 |  | Associate board’s sole function is fundraising
Task | Start date | Deadline | Owners | Notes
Technology
Identify hardware and network requirements | 2017-09-17 | 2017-03-18 | DT | Initial requirements identified, will be reviewed once facility is secured; MXO Tech has provided detailed overview of hardware needs
Create technology plan | 2017-09-17 | 2017-11-17 | DT/P | Technology plan will incorporate initial requirements and facility needs
Research vendors & obtain SIS quotes | 2017-02-17 | 2017-02-18 | P | Process initiated pre-Tier I application
Schedule and execute SIS training sessions | 2017-06-18 | 2017-07-18 | P
Obtain quotes for website | 2017-03-17 | 2017-09-17 | DT
Website development & launch | 2017-02-17 | 2017-02-18 | DT | Include parent, teacher and student portals
Purchase hardware and software | 2017-06-18 | 2017-07-18 | BM
Purchase and test internet services | 2017-06-18 | 2017-06-18 | BM
Ensure student data security systems are in place | 2017-03-18 | 2017-04-18 | P/BM
Apply for e-rate | 2017-09-17 | 2017-03-18 | BM | e-rate consultant: Jane Kratochvil/Infinite Connections, Inc.
Install technology and equipment | 2017-06-18 | 2017-07-18 | BM/OM | Such as computers, projectors, phones, PA system (if adopted)
Lease copiers | 2017-05-18 | 2017-06-18 | BM
Task | Start date | Deadline | Owners | Notes
Food program
Identify food service requirements | 2017-01-18 | 2017-04-18 | P/DT
Obtain vendor quotes and select vendor through a bid process | 2017-09-16 | 2017-04-18 | DT/P | Began research in 2016; reviewed proposals from Gourmet Gorilla, Sodexo
Distribute, collect and submit forms to determine USDA free/reduced price meals program eligibility | 2017-04-18 | 2017-08-18 | P/SC
Review food service plan with vendor | 2017-04-18 | 2017-06-18 | P/OM
Set menu and meal schedules | 2017-06-18 | 2017-06-18 | P/OM
Develop dining hall procedure, rules and expectations | 2017-06-18 | 2017-06-18 | FM

## Tasks 2018-2019
MONTH | Date | OUTCOME OR PARAMETER | FREQUENCY | BOARD REQUIRED ACTION | AGENDA ITEM | Origin | DELEGATED TO: | BOARD OR MGMT METRIC?
JUL | n/a | parameter | quarterly | Receive | Full financial report Q4 | other | Board Treasurer | board
JUL | third Thur | parameter | annually | Confirmation | Board applicants/nominations received | bylaws | Governance Committee | board
JUL | n/a | parameter | every other month | Conduct | Check in w/authorizer/report to board | other | Chair | board
AUG | n/a | parameter | annually | Conduct | Officer elections | bylaws | Entire Board | board
AUG | n/a | parameter | annually | Confirmation | Audit/Form 990 processes have commenced | IRS | Finance Committee | management
AUG | n/a | parameter | annually | Conduct | Board member elections | bylaws | Governance Committee | board
AUG | n/a | outcome | annually | Evaluate | State test results | statute | Academic Excellence Committee | management
AUG | n/a | parameter | other | Evaluate | Compliance with internal control policy | board policy | Governance Committee | management
SEPT | n/a | parameter | every other month | Conduct | Check in w/authorizer/report to board | other | Chair | board
SEPT | n/a | outcome | other | Benchmark | MAP Administration #1 | charter | Board Treasurer | management
SEPT | n/a | parameter | annually | Conduct | New member orientation | board policy | Governance Committee | board
SEPT | n/a | parameter | annually | Confirmation | Publicly announce board election results | bylaws | Governance Committee | board
OCT | n/a | outcome | annually | Confirmation | State test was administered w/o problems | statute | Academic Excellence Committee | management
OCT | n/a | parameter | quarterly | Receive | Full financial report Q1 | other | Board Treasurer | board
OCT | n/a | parameter | annually | Conduct | Board & Staff Social mixer | other | Governance Committee | board
OCT | n/a | parameter | annually | Review | Form 990 (non-profit tax return) | IRS | Finance Committee | board
NOV | 15 | parameter | annually | Approve | Form 990 (non-profit tax return) | IRS | Finance Committee | board
NOV | n/a | parameter | every other month | Conduct | Check in w/authorizer/report to board | other | Chair | board
JAN | n/a | parameter | quarterly | Receive | Full financial report Q2 | other | Board Treasurer | board
JAN | n/a | parameter | every other month | Conduct | Check in w/authorizer/report to board | other | Chair | board
JAN | n/a | parameter | other | Evaluate | Compliance with internal control policy | board policy | Governance Committee | management
JAN | n/a | outcome | other | Benchmark | MAP Administration #2 | charter | Academic Excellence Committee | management
MAR | n/a | parameter | every other month | Conduct | Check in w/authorizer/report to board | other | Chair | board
MAR | n/a | parameter | annually | Confirmation | Auditor RFPs announced | other | Finance Committee | board
APR | n/a | parameter | other | Evaluate | Compliance with internal control policy | board policy | Governance Committee | management
APR | n/a | parameter | quarterly | Receive | Full financial report Q3 | other | Board Treasurer | board
MAY | n/a | parameter | annually | Approve | Auditor selection | other | Entire Board | board
MAY | n/a | parameter | every other month | Conduct | Check in w/authorizer/report to board | other | Chair | board
MAY | n/a | outcome | annually | Evaluate | Graduation rates | charter | Academic Excellence Committee | management
MAY | n/a | parameter | annually | Approve | Faculty & staff new hire contracts | board policy | Governance Committee | management
MAY | n/a | outcome | other | Evaluate | MAP Administration #3 | charter | Academic Excellence Committee | management