## CFA
Non-Academic / Operations Start-up Plan | Position Responsible | 2013-09-01 | 2013-10-01 | 2013-11-01 | 2013-12-01 | 2014-01-01 | 2014-02-01 | 2014-03-01 | 2014-04-01 | 2014-05-01 | 2014-06-01 | 2014-07-01 | 2014-08-01 | 2014-09-01
|  |  | KEY: | C | Complete |  |  | Anticipated
Governance & Organization
Incorporation
Articles of Incorporation / state filings | Executive Director | bar: 2013-09-01
Federal EIN | Executive Director | bar: 2013-09-01
501c3 determination | Executive Director | bar: 2013-09-01
Secure all business & board insurance | Executive Director | bar: 2013-11-01; 2014-03-01
Amend articles for permanent address | Executive Director | bar: 2014-09-01
Governance
Draft board profile | Board Chair | bar: 2013-09-01
Draft by laws | Board Chair | bar: 2013-09-01
Establish board calendar | Board Chair | bar: 2013-09-01
Develop compensation strategy | Board Members | bar: 2013-09-01
Recruit founding board members | Board Chair | bar: 2013-09-01
Execute board conflict of interest policy | Board Chair | bar: 2013-10-01
Determine board governance structure | Board Chair | bar: 2013-10-01
Define committees & draft duties | Board Chair | bar: 2013-10-01
Define officer positions & draft duties | Board Chair | bar: 2013-10-01
Elect Founding Board officers | Board Chair | bar: 2013-10-01
Obtain legal counsel | Board Chair | bar: 2013-10-01
Establish separation of duties | Board Chair | bar: 2013-10-01
Develop contract with Exec. Director | Board Members | bar: 2013-12-01
Develop Exec Director compensation plan | Board Members | bar: 2013-12-01
Recruit members of the Board of Directors | Board Governance Comm. | bar: 2014-02-01
Develop board self-evaluation process | Board Chair | bar: 2014-03-01
Develop board training plan | Board Chair | bar: 2014-03-01
Develop board manual | Board Chair | bar: 2014-03-01
Transition from Founding to Permanent Board | Board Chair | bar: 2014-03-01
Induct new board members | Board Governance Comm. | bar: 2014-03-01
Execute conflict of interest policies | Board Governance Comm. | bar: 2014-03-01
Elect Board Officers | Board Members | bar: 2014-03-01
Form Board Committees | Board Chair | bar: 2014-03-01
Re-establish board meeting calendar | Board Chair | bar: 2014-03-01
Develop evaluation process for Exec. Dir. | Board Chair | bar: 2014-09-01
Full board training program | Board Chair | bar: 2014-09-01
Charter Authorization
Draft Tier 1 Proposal | Executive Director | bar: 2013-09-01
CPS interview | Executive Director | bar: 2013-10-01
Community input / forum | Executive Director | bar: 2013-10-01 to 2013-11-01
Integrate feedback and community input | Executive Director | bar: 2013-10-01 to 2013-11-01
Draft Tier 2 Proposal | Executive Director | bar: 2013-12-01
Community meeting | Executive Director | bar: 2013-12-01
Public hearing | Executive Director | bar: 2014-01-01
CPS decision | Executive Director | bar: 2014-01-01
Legal / board review of contract | Executive Director | bar: 2014-01-01; 2014-08-01 to 2014-09-01
Execute contract for school | Executive Director | bar: 2014-09-01
Development / Fundraising
Research foundations & corporations | Board Dev Committee | bar: 2013-09-01 to 2013-10-01
Create prospects list from research | Board Dev Committee | bar: 2013-09-01 to 2013-10-01
Develop fundraising plan and strategy | Board Dev Committee | bar: 2013-09-01 to 2013-10-01
Apply for CPS start-up grant | Executive Director | bar: 2013-09-01 to 2013-10-01
Develop standard development deck | Executive Director | bar: 2013-10-01
Conduct board fundraising programs/outreach | Board Dev Committee
Submit round of corporate grant applications | Board Dev Committee | bar: 2013-12-01 to 2014-09-01
Non-Academic Operations
School Scheduling
Create Annual Calendar | Campus Leadership | bar: 2014-01-01
Create Daily Schedule | Campus Leadership | bar: 2014-01-01
Create Monthly Calendar | Campus Leadership | bar: 2014-01-01
Finance & Accounting
Finalize job description for DFO | Executive Director | bar: 2013-09-01; 2014-01-01
Develop start-up budget and cash flow forecast | DFO | bar: 2013-09-01
Develop business plan & 5 year forecast | DFO | bar: 2013-09-01
Open bank account and order checks | Executive Director | bar: 2013-10-01
Identify check writers and signatories | ED & DFO | bar: 2013-10-01; 2014-01-01
Hire DFO | Executive Director | bar: 2013-12-01
Develop 5 year contingency budgets | DFO | bar: 2014-01-01
Hire payroll processing company | DFO | bar: 2014-01-01
Finalize internal controls and policies | DFO | bar: 2014-01-01
Asset Tracking | DFO | bar: 2014-01-01
Banking | DFO | bar: 2014-01-01
Credit Cards | DFO | bar: 2014-01-01
Documentation, Filing, Storage and Disposal | DFO | bar: 2014-01-01
Petty Cash | DFO | bar: 2014-01-01
Reimbursement | DFO | bar: 2014-01-01
Segregation of Duties | DFO | bar: 2014-01-01
Establish chart of accounts | DFO | bar: 2014-01-01
Develop grant reporting requirements | DFO | bar: 2014-01-01
Build detailed procurement list by item | DFO | bar: 2014-02-01
Build list of vendors and obtain quotes | DFO | bar: 2014-02-01
Obtain quotes for bookkeeping, audit & payroll | DFO | bar: 2014-02-01
Hire accounting firm | DFO | bar: 2014-02-01
Purchase and implement accounting software | DFO | bar: 2014-02-01
Develop standard forms (PO's, contracts) | DFO | bar: 2014-02-01
Develop monthly board reporting format | DFO | bar: 2014-03-01
Obtain line of credit | DFO | bar: 2014-05-01
Finalize year 1 school budgets | DFO | bar: 2014-06-01
Integrate HR data into payroll system | DFO | bar: 2014-07-01 to 2014-08-01
Form IRS 990 | DFO | bar: 2014-08-01
Facility Operations
Meet with facility advisors | Executive Director | bar: 2013-09-01
Identify sites | Executive Director | bar: 2013-09-01 to 2013-11-01
Identify renovations most conducive to learning | Executive Director | bar: 2013-10-01 to 2013-11-01
Necessary facility inspections initiated | ED & DFO | bar: 2013-12-01 to 2014-01-01
Solicit bids for renovations and improvements | DFO | bar: 2014-02-01 to 2014-03-01
Conduct renovations | DFO | bar: 2014-04-01 to 2014-06-01
Establish property insurances | DFO | bar: 2014-04-01
Address building security issues | DFO | bar: 2014-04-01 to 2014-06-01
Determine signage requirements | DFO | bar: 2014-04-01
Obtain quotes for school signages | DFO | bar: 2014-05-01
Post school signages | DFO | bar: 2014-06-01
Determine storage needs/plan | DFO | bar: 2014-06-01
Assign classrooms | Campus Leadership | bar: 2014-07-01
Assign office spaces | DFO | bar: 2014-07-01
Deliver furniture and equipment | DFO | bar: 2014-08-01
Common space set-up | DFO | bar: 2014-08-01
Classroom set-up | Campus Leadership | bar: 2014-08-01
Computer lab set-up | Campus Leadership | bar: 2014-08-01
Beautification - volunteer work | DFO | bar: 2014-08-01
Final repair and janitorial prep for first days | DFO | bar: 2014-08-01 to 2014-09-01
Security & Safety
Liaise with local police for crosswalk | DFO | bar: 2014-03-01 to 2014-08-01
Outline student / visitor traffic flows | Campus Leadership | bar: 2014-06-01
Outline security procedures | DFO & Campus Leadership | bar: 2014-06-01
Develop emergency communication process | DFO & Campus Leadership | bar: 2014-06-01
Develop safety and emergency handbook | DFO & Campus Leadership | bar: 2014-06-01
Create security job descriptions | DFO & Campus Leadership | bar: 2014-06-01
Establish evacuation plan for all rooms | DFO & Campus Leadership | bar: 2014-07-01 to 2014-09-01
Begin work with security officer(s) | DFO | bar: 2014-07-01 to 2014-08-01
Set expectations with security officers | DFO & Campus Leadership | bar: 2014-07-01 to 2014-08-01
Provide staff with safety/first aid training | DFO | bar: 2014-08-01 to 2014-09-01
Schedule and test fire drills | DFO & Campus Leadership | bar: 2014-09-01
Technology
Research vendors and obtain SIS quotes | DFO | bar: 2013-10-01
Obtain domain name | DFO | bar: 2013-10-01
Obtain quotes for website | DFO | bar: 2013-10-01
Build out website | DFO | bar: 2013-11-01
Identify hardware & network requirements | DFO | bar: 2014-01-01
Select Student Information System(s) | DFO & Campus Leadership | bar: 2014-02-01
Procure hardware | DFO | bar: 2014-03-01 to 2014-08-01
Implement SIS with student data | DFO & Campus Leadership | bar: 2014-04-01 to 2014-08-01
Student data requirements | DFO & Campus Leadership
Attendance | DFO & Campus Leadership | bar: 2014-05-01
Food Service | DFO & Campus Leadership | bar: 2014-05-01
Special Education | DFO & Campus Leadership | bar: 2014-05-01
Student Discipline | DFO & Campus Leadership | bar: 2014-05-01
Health/Immunization/Related Policies | DFO & Campus Leadership | bar: 2014-05-01
Processing New Students | DFO & Campus Leadership | bar: 2014-05-01
Emergency Contact Information | DFO & Campus Leadership | bar: 2014-05-01
Transportation
Review IEP transportation needs | SPED Lead Teacher | bar: 2014-06-01
Communication of routes, rules, policy | SPED Lead Teacher | bar: 2014-08-01
Procure public transp. cards, as necessary | DFO | bar: 2014-08-01 to 2014-09-01
Food Services
Identify food service requirements | DFO | bar: 2014-03-01
Obtain vendor quotes | DFO | bar: 2014-04-01
Select vendor | DFO | bar: 2014-05-01
Review food service plan with vendor | DFO | bar: 2014-06-01 to 2014-07-01
Set meal schedules | DFO | bar: 2014-08-01 to 2014-09-01
Set expectations with food service staff | DFO | bar: 2014-08-01 to 2014-09-01
Set menus | DFO | bar: 2014-08-01 to 2014-09-01
Personnel
Policies & Procedures
Develop draft of personnel policies | DFO | bar: 2014-01-01
Develop hiring policies and procedures | DFO | bar: 2014-01-01
Draft employee manual / handbook | DFO | bar: 2014-01-01 to 2014-02-01
Contract for background checks | DFO | bar: 2014-01-01
Compensation
Outline compensation strategy | Executive Director | bar: 2013-09-01
Research other schools compensation | Executive Director | bar: 2013-09-01
Integrate compensation into budget | Executive Director | bar: 2013-09-01; 2014-06-01
Staffing
Determine start-up staffing needs | Executive Director | bar: 2013-09-01
Write Campus Leadership job description | Executive Director | bar: 2013-09-01
Execute Exec Director contract | Board Members | bar: 2013-12-01
Execute Campus Leadership contract | Executive Director | bar: 2013-12-01
Hire planning year staff | Executive Director | bar: 2013-12-01
Draft employee contracts with counsel | DFO | bar: 2014-01-01
Write all school job descriptions | ED & Campus Leadership | bar: 2014-01-01
Post job descriptions and recruit teachers | Campus Leadership | bar: 2014-01-01
Teacher interviews and site visits / referrals | Campus Leadership | bar: 2014-03-01 to 2014-05-01
Conduct background checks | DFO | bar: 2014-05-01
Hire teachers and other instructional staff | Campus Leadership | bar: 2014-05-01 to 2014-06-01
HR Data
Create personnel files | DFO | bar: 2014-07-01
Develop HR database | DFO | bar: 2014-07-01
Integrate HR data into payroll system | DFO | bar: 2014-08-01
Health & Welfare Benefits
Hire insurance broker | DFO | bar: 2014-01-01
Finalize benefits package design | DFO | bar: 2014-02-01
Obtain quotes for health benefits | DFO | bar: 2014-02-01
Secure health benefit package | DFO | bar: 2014-02-01
Finalize retirement program design | DFO | bar: 2014-03-01
Finalize PTO, vacation, leave policies | DFO | bar: 2014-03-01
Professional Development
Finalize partnerships to support PD efforts | Executive Director | bar: 2013-12-01 to 2014-01-01
Campus Leadership training program | Campus Leadership | bar: 2014-02-01
Develop teacher induction program | Campus Leadership | bar: 2014-05-01
Design personnel evaluation forms | Campus Leadership | bar: 2014-06-01
Conduct teacher PD | Campus Leadership | bar: 2014-07-01 to 2014-08-01
Conduct teacher orientation program | Campus Leadership | bar: 2014-07-01 to 2014-08-01
Administrative Offices Operations
Define office staff roles and responsibilities | DFO | bar: 2014-01-01 to 2014-02-01
Develop office operating procedures | DFO | bar: 2014-04-01 to 2014-05-01
Visitors | DFO | bar: 2014-04-01
Phone answering | DFO | bar: 2014-04-01
Medical procedures | DFO | bar: 2014-05-01
Records management | DFO | bar: 2014-05-01
Academic Operations
Student Outreach & Recruitment Activities
Identify community characteristics and needs | Executive Director | bar: 2013-09-01
Research student mobility trends | Executive Director | bar: 2013-09-01
Develop school and agency contacts | Executive Director | bar: 2013-09-01 to 2013-11-01
Set recruitment goals and timelines | Executive Director | bar: 2013-09-01 to 2013-11-01
Develop advertising | Campus Leadership | bar: 2013-11-01 to 2013-12-01
Develop student recruitment materials | Campus Leadership | bar: 2013-11-01 to 2013-12-01
Develop mass mailing | Campus Leadership | bar: 2014-01-01
Develop plan and/or maps for door to door canvassing | Campus Leadership | bar: 2014-01-01
Research lottery legal requirements | Campus Leadership | bar: 2014-01-01
Research other school lottery practices | Campus Leadership | bar: 2014-01-01
Schedule lottery | Campus Leadership | bar: 2014-01-01
Schedule information sessions for parents | Campus Leadership | bar: 2014-03-01
Schedule presentations to schools & agencies | Campus Leadership | bar: 2014-03-01
Execute mass mailings and advertising | Campus Leadership | bar: 2014-03-01
Execute door to door campaign | Campus Leadership | bar: 2014-03-01
Hold information sessions | ED & Campus Leadership | bar: 2014-03-01
Present at scheduled events | ED & Campus Leadership | bar: 2014-03-01
Develop student application and materials | Campus Leadership | bar: 2014-03-01
Set up student application database for lottery | Campus Leadership | bar: 2014-03-01
Develop enrollment materials | Campus Leadership | bar: 2014-03-01
Hold lottery | Campus Leadership | bar: 2014-04-01
Distribute acceptance and waiting list letters | Campus Leadership | bar: 2014-04-01
Distribute enrollment package to confirmed families | Campus Leadership | bar: 2014-05-01
Schedule student registrations | Campus Leadership | bar: 2014-05-01
Manage on-going admissions | Campus Leadership | bar: 2014-07-01
Align data in IMPACT & SIS | Campus Leadership | bar: 2014-08-01 to 2014-09-01
Accountability
Schedule Academic Committee meetings | Executive Director | bar: 2014-03-01
Finalize achievement goals for Year 1 | Executive Director | bar: 2014-04-01
Finalize financial and ops goals for Year 1 | Executive Director | bar: 2014-04-01
Special Education
Hire SPED Lead Teacher | Campus Leadership | bar: 2014-06-01
Request IEP copies | Campus Leadership | bar: 2014-07-01
Determine student population needs | Campus Leadership | bar: 2014-07-01
Track accepted students with IEPs in IMPACT | Campus Leadership | bar: 2014-08-01
Schedule students to ensure meeting IEPs | Campus Leadership | bar: 2014-08-01
Collect all of student files from previous schools | SPED Lead Teacher | bar: 2014-08-01
Setup co-teaching common planning meetings | Campus Leadership | bar: 2014-08-01 to 2014-09-01
Create annual review and eval timelines | Campus Leadership | bar: 2014-08-01 to 2014-09-01
Distribute IEP information to teachers | SPED Lead Teacher | bar: 2014-08-01 to 2014-09-01
Review accommodations with teachers | SPED Lead Teacher | bar: 2014-08-01 to 2014-09-01
Community
Meet with key CBOs and FBOs | Executive Director | bar: 2014-02-01
Attend important community events | Executive Director | bar: 2014-02-01
Builld relationship with police department | Executive Director | bar: 2014-04-01
Seek partners for services & programs | Executive Director | bar: 2014-04-01
Create safe passage plan | DFO | bar: 2014-06-01 to 2014-09-01